## Sheet1
Task | Start Date | End Date | Duration | Weeks
Week1 |  |  |  | 1
Confirmed Group memebers | 2017-09-12 | 2017-09-19 | 7 | 2
Present the topic and interview | 2017-09-19 | 2017-09-26 | 7 | 3
First presentation interview | 2017-09-26 | 2017-10-03 | 7 | 4
Begin implentation on users login & transitions | 2017-10-03 | 2017-10-10 | 7 | 5
Begin basic construct on database | 2017-10-10 | 2017-10-17 | 7 | 6
Present the project to the class | 2017-10-17 | 2017-10-24 | 7 | 7
Contiuned database implentation and server communication | 2017-10-24 | 2017-10-31 | 7 | 8
Preperation for beta release/refining graphics | 2017-10-31 | 2017-11-07 | 7 | 9
Third presentation | 2017-11-07 | 2017-11-14 | 7 | 10
Refining beta operations | 2017-11-14 | 2017-11-21 | 7 | 11
Preperation for 4th interview | 2017-11-21 | 2017-11-28 | 7 | 12
Fourth interview | 2017-11-28 | 2017-12-05 | 7 | 13
Final debugging stage | 2017-12-05 | 2017-12-12 | 7 | 14
Final project submmision | 2017-12-12 | 2017-12-19 | 7 | 15